National Association for Hospital Education Development Plan 2023-24

Context and aims

Overall aims: - To work collaboratively to secure outstanding standards of education for the children and young people we support who are temporarily or permanently disadvantaged by illness or other medical / mental health conditions. - To actively promote children and young people’s entitlement to high quality and breadth of educational opportunities, regardless of their age or where they live. - To advocate, challenge and collaborate with educational partners in order to contribute to an equal and inclusive educational offer for all children. - To support parents, clinicians and other professionals working in our sector to ensure the very best outcomes for our children and young people. - To raise awareness and influence policy at a national level to ensure equality of opportunity for our children and young people.

| Priority: To develop the structures and finances so that NAHE can be sustainable for the future |  |  | Why is this a priority? As NAHE is an organisation currently run by volunteers, we need to consider our finance model so that the organisation is sustainable for the future |  |  |  |
| --- | --- | --- | --- | --- | --- | --- |
| Actions | By who? | By when? | Success criteria & evidence | Anticipated impact / KPIs | Progress comment / update (RAG rated) | Resources / costs |
| To continue to grow and develop the organisation | All directors | Ongoing | Membership grows year on year. | Membership growth ensures consistent funding stream to sustain the organisation |  | Admin/finance support Director time |
| To develop a financial strategy and clear business plan for the future | All directors | Oct 2024 | Financial strategy and BCP in place | To ensure that the organisation is sustainable for the future, both financially and personnel |  | Admin/finance support Director time |
| To sustain current members | All directors | Ongoing | Current members continue to maintain their membership | Membership builds from current membership base |  | Admin/finance support |
| To plan for the succession of key directors, including the chair | All directors | Final plan Sept 2024 | Succession plan in place and period of transition planned | Organisation is sustainable ensuring smooth transitions to new personnel |  | Director time |
| To publicise a clear set of definitions for the different parts that make up ‘hospital education’ | HEWG workstream | March 2024 | Clear definitions of hospital education, medical AP and home tuition services published | Clearer for LAs to develop appropriate funding mechanisms, support work on green paper |  | HEWG workstream time DfE time |
| To publicise and raise the profile of NAHE on a national level | All members | Ongoing | NAHE representation at all key groups and organisations. Article from members in education journals and publications | NAHE nationally known and acknowledged |  | Members time |

| Priority: To continue to embed and develop the peer support networks |  |  | Why is this a priority? This will allow staff working in hospital education to discuss key issues and share best practice which supports improved outcomes for children with medical needs. Staff in some provisions may be isolated and require support from peers within the sector. |  |  |  |
| --- | --- | --- | --- | --- | --- | --- |
| Actions | By who? | By when? | Success criteria & evidence | Anticipated impact / KPIs | Progress comment / update (RAG rated) | Resources / costs |
| Embed current networks and establish new where there are none at present, including cross phase | Directors | March 2024 | Groups identified and met. Future working relationships established. | Good practice for subjects is shared and disseminated. Staff feel supported |  | Staff / admin time |
| Develop networks for staff working in similar settings e.g. paediatric hospitals, CAMHS Units, Medical AP | Directors | March 2023 | Network groups established, meeting regularly | More refined sharing of practice for staff in similar settings |  | Staff time Poss venue costs |
| Develop a peer review system for hospital education provisions | Directors | March 2024 | Peer review cycle trialled with a group of centres. Peer reviews / evaluations take place and the system agreed for roll out. | System of peer review allows centres to quality assure and improve outcomes for pupils. Supports other external review processes. |  | Staff time for school visits |
| Develop the members area of the NAHE website | All | Ongoing | Feedback from stakeholders / interaction with the website. Increased membership. | Staff feel supported and able to share key information leading to improved outcomes. |  | Within website costs |
| Develop a set of ‘best practice’ guidelines for mainstream staff | Directors and subject networks | Ongoing cycle of publications July 2024 | Set of best practice guides available e.g. reintegration | NAHE members have a document to refer external quality assurers and mainstream settings to better understand our context. |  | Staff time |

| Priority: To ensure equality of provision for children with medical needs across the country |  |  | Why is this a priority? There is variability across the country in the provision for children missing education due to ill health. This includes funding, access to teaching, level of support LAs provide, number of hours education provided, etc. We have a role to ensure that any further proposals do not further disadvantage our pupils. |  |  |  |
| --- | --- | --- | --- | --- | --- | --- |
| Actions | By who? | By when? | Success criteria & evidence | Anticipated impact / KPIs | Progress comment / update (RAG rated) | Resources / costs |
| Work with the DFE to raise the profile of the sector and our pupil cohorts | Chair & directors | Ongoing | The challenges experienced by our pupils is better understood by DfE | Decisions made on policy will consider the needs of our pupils |  | Staff time |
| To work with the DfE and Change Partnership Programme leaders to ensure that proposals in the Green Paper meet the needs of our pupils | HEWG Workstream members | July 2024 | Clear set of criteria for implementing the proposals within the green paper relating specifically to our pupils | Our pupils will not be disadvantaged by any future proposals for changes to the sectors |  | Staff time |
| To write a manifesto for education for our pupils and share with political party education ministers | Directors | March 2024 | Manifesto in place and shared with political parties | Politicians are aware of the challenges faced by our pupils and solutions to promote equity. |  | Directors time |
| To encourage research projects within the sector | All members | July 24 and ongoing | Increase in availability of research pertinent to our pupils and sector | More robust evidence base in place for proven successful approaches for our pupils |  | Staff time |
| NAHE represented on other national / regional groups where we do not yet have a presence | All | Ongoing | NAHE represented on groups to raise the profile of pupils with medical needs at a national level | Raises awareness of NAHE, better networking improves outcomes for children. Able to have a voice at government level and influence policy. |  | Joining fees, staff time |